## Gantt GeoNature
Flight delays project
Gantt diagram
Project phase | Start | End
Preparation | 2021-02-26 | 2021-02-27
Data validation | 2021-02-28 | 2021-02-28
Present initial plan | 2021-03-01 | 2021-03-01
Initial data investigations | 2021-03-01 | 2021-03-02
Analysis for report | 2021-03-03 | 2021-03-03
Modelling for report | 2021-03-04 | 2021-03-06
First 1:1 with instructors | 2021-03-04 | 2021-03-04
Write report | 2021-03-07 | 2021-03-07
Write presentation | 2021-03-08 | 2021-03-08
Other documentation | 2021-03-08 | 2021-03-08
Second 1:1 with instructors | 2021-03-08 | 2021-03-08
Contingency | 2021-03-09 | 2021-03-09
Submission | 2021-03-10 | 2021-03-10
Presentation | 2021-03-11 | 2021-03-11
|  |  | Project phase | Task | Projected Start Date | Projected End Date | Milestone? | Duration (Days) | Actual Completion Date
|  |  | Preparation | Read project brief and associated documentation | 2021-02-26 | 2021-02-27 |  | 2 | 2021-02-27
|  |  | Preparation | Create GitHub Repo, send link to instructors | 2021-02-26 | 2021-02-27 |  | 2 | 2021-02-27
|  |  | Preparation | Load data provided with brief to understand structure | 2021-02-26 | 2021-02-27 |  | 2 | 2021-02-27
|  |  | Preparation | Understand data provided with brief - read data dictionaries | 2021-02-26 | 2021-02-27 |  | 2 | 2021-02-27
|  |  | Preparation | Background reading | 2021-02-26 | 2021-02-27 |  | 2 | 2021-02-27
|  |  | Preparation | Identify any supplementary data required based on initial view of data supplied with brief | 2021-02-26 | 2021-02-27 |  | 2 | 2021-02-27
|  |  | Preparation | Create brief document outlining plan - for PDA and CodeClan instructors | 2021-02-26 | 2021-02-27 |  | 2 | 2021-02-27
|  |  | Data validation | Confirm how to join data tables | 2021-02-28 | 2021-02-28 |  | 1 | 2021-02-27
|  |  | Data validation | Identify key fields likely to be used in analysis | 2021-02-28 | 2021-02-28 |  | 1 | 2021-02-28
|  |  | Data validation | Dates/times - confirm necessary transformations e.g. timezones | 2021-02-28 | 2021-02-28 |  | 1 | 2021-03-01
|  |  | Data validation | Identify any other transformations required | 2021-02-28 | 2021-02-28 |  | 1 | 2021-02-27
|  |  | Data validation | Identify any derived fields required | 2021-02-28 | 2021-02-28 |  | 1 | 2021-03-01
|  |  | Data validation | Create a cleaning script to join and transform data | 2021-02-28 | 2021-02-28 |  | 1 | 2021-01-28
|  |  | Milestone | Cleaning script complete | 2021-03-01 | 2021-03-01 | Yes | - | 2021-03-01
|  |  | Present initial plan | Present initial plan to instructors | 2021-03-01 | 2021-03-01 | Yes | - | 2021-03-01
|  |  | Initial data investigations | Exploratory analysis of data to identify insights and trends | 2021-03-01 | 2021-03-02 |  | 2 | 2021-03-01
|  |  | Initial data investigations | Create workings file with subsets/data which could be used in the final report | 2021-03-01 | 2021-03-02 |  | 2 | 2021-03-03
|  |  | Initial data investigations | Source any supplementary data required after initial investigations | 2021-03-01 | 2021-03-02 |  | 2 | 2021-03-01
|  |  | Initial data investigations | Identify variables which could be used in modelling | 2021-03-01 | 2021-03-02 |  | 2 | 2021-03-02
|  |  | Initial data investigations | Update cleaning script with any changes required after initial investigations | 2021-03-01 | 2021-03-02 |  | 2 | 2021-03-02
|  |  | Milestone | Initial investigations complete | 2021-03-03 | 2021-03-03 | Yes | - | 2021-03-03
|  |  | Analysis for report | Create draft report with data and visualisations | 2021-03-03 | 2021-03-03 |  | 1 | 2021-03-03
|  |  | Modelling for report | Create explanatory model in report | 2021-03-04 | 2021-03-06 |  | 3 | 2021-03-08
|  |  | First 1:1 with instructors | First 1:1 with instructors | 2021-03-04 | 2021-03-04 | Yes | - | 2021-03-04
|  |  | Write report | Write report | 2021-03-07 | 2021-03-07 |  | 1 | 2021-03-08
|  |  | Milestone | Report complete | 2021-03-08 | 2021-03-08 | Yes | - | 2021-03-08
|  |  | Write presentation | Write presentation | 2021-03-08 | 2021-03-08 |  | 1
|  |  | Milestone | Presentation complete | 2021-03-09 | 2021-03-09 | Yes | -
|  |  | Other documentation | README and any other documentation req'd on GitHub | 2021-03-08 | 2021-03-08 |  | 1
|  |  | Other documentation | PDA documentation | 2021-03-08 | 2021-03-08 |  | 1
|  |  | Other documentation | Practice giving presentation | 2021-03-08 | 2021-03-08 |  | 1
|  |  | Second 1:1 with instructors | Second 1:1 with instructors | 2021-03-08 | 2021-03-08 | Yes | - | 2021-03-08
|  |  | Contingency | Contingency for revisions, corrections etc | 2021-03-09 | 2021-03-09 |  | 1
|  |  | Submission | Submission | 2021-03-10 | 2021-03-10 | Yes | -
|  |  | Presentation | Presentation | 2021-03-11 | 2021-03-11 | Yes | -
|  |  | Check: | Task | Start Date | Duration | u
|  |  | TRUE | Read project brief and associated documentation | 44253 | 2 | #N/A
|  |  | TRUE | Create GitHub Repo, send link to instructors | 44253 | 2 | #N/A
|  |  | TRUE | Load data provided with brief to understand structure | 44253 | 2 | #N/A
|  |  | TRUE | Understand data provided with brief - read data dictionaries | 44253 | 2 | #N/A
|  |  | TRUE | Background reading | 44253 | 2 | #N/A
|  |  | TRUE | Identify any supplementary data required based on initial view of data supplied with brief | 44253 | 2 | #N/A
|  |  | TRUE | Create brief document outlining plan - for PDA and CodeClan instructors | 44253 | 2 | #N/A
|  |  | TRUE | Confirm how to join data tables | 44255 | 1 | #N/A
|  |  | TRUE | Identify key fields likely to be used in analysis | 44255 | 1 | #N/A
|  |  | TRUE | Dates/times - confirm necessary transformations e.g. timezones | 44255 | 1 | #N/A
|  |  | TRUE | Identify any other transformations required | 44255 | 1 | #N/A
|  |  | TRUE | Identify any derived fields required | 44255 | 1 | #N/A
|  |  | TRUE | Create a cleaning script to join and transform data | 44255 | 1 | #N/A
|  |  | TRUE | Cleaning script complete | 44256 | #N/A | 1
|  |  | TRUE | Present initial plan to instructors | 44256 | #N/A | 1
|  |  | TRUE | Exploratory analysis of data to identify insights and trends | 44256 | 2 | #N/A
|  |  | TRUE | Create workings file with subsets/data which could be used in the final report | 44256 | 2 | #N/A
|  |  | TRUE | Source any supplementary data required after initial investigations | 44256 | 2 | #N/A
|  |  | TRUE | Identify variables which could be used in modelling | 44256 | 2 | #N/A
|  |  | TRUE | Update cleaning script with any changes required after initial investigations | 44256 | 2 | #N/A
|  |  | TRUE | Initial investigations complete | 44258 | #N/A | 1
|  |  | TRUE | Create draft report with data and visualisations | 44258 | 1 | #N/A
|  |  | TRUE | Create explanatory model in report | 44259 | 3 | #N/A
|  |  | TRUE | First 1:1 with instructors | 44259 | #N/A | 1
|  |  | TRUE | Write report | 44262 | 1 | #N/A
|  |  | TRUE | Report complete | 44263 | #N/A | 1
|  |  | TRUE | Write presentation | 44263 | 1 | #N/A
|  |  | TRUE | Presentation complete | 44264 | #N/A | 1
|  |  | TRUE | README and any other documentation req'd on GitHub | 44263 | 1 | #N/A
|  |  | TRUE | PDA documentation | 44263 | 1 | #N/A
|  |  | TRUE | Practice giving presentation | 44263 | 1 | #N/A
|  |  | TRUE | Second 1:1 with instructors | 44263 | #N/A | 1
|  |  | TRUE | Contingency for revisions, corrections etc | 44264 | 1 | #N/A
|  |  | TRUE | Submission | 44265 | #N/A | 1
|  |  | TRUE | Presentation | 44266 | #N/A | 1
Formulas:
End = [End, row below]-1
Projected Start Date = IF([Project phase]= "Milestone",[Projected End Date, row above]+1,VLOOKUP([Project phase],A5:C20,2,0))
Projected End Date = IF([Project phase]= "Milestone",[Projected End Date, row above]+1,VLOOKUP([Project phase],A5:C20,3,0))

## Instructions
Instructions
Pour modifier les dates: saisissez-les dans les colonnes C et D du tableau qui commence dans la cellule A6
- Notez que les cellules jaunes sont liées à une étape précédente - soit un lien direct vers une cellule précédente, soit une formule qui ajoute le nombre de jours que la tâche devrait durer
- Si vous préférez, ces formules peuvent être remplacées en tapant simplement les dates
Si vous ajoutez une ligne supplémentaire à ce tableau: Vous devez également mettre à jour le tableau caché sous le diagramme.
- Ce tableau supplémentaire formate les données afin qu'elles puissent être affichées correctement dans le diagramme
- Faites glisser le diagramme vers la droite pour afficher ce tableau
- Il vous suffit de faire glisser les formules dans la ligne supérieure du tableau masqué pour couvrir le même nombre de lignes dans le tableau principal
Vous devez ensuite modifier le diagramme pour qu'il inclue les nouvelles lignes:
- Cliquez avec le bouton droit sur le diagramme
- Cliquez sur "sélectionner les données"
- Modifiez la plage de données afin qu'elle couvre toutes les lignes de la table "caché"